Action Plan 2021/2022

| Action | Time Scale | Monitored by who | Resources needed | Completed |
| --- | --- | --- | --- | --- |
| Meet with AS to gather information about where the school is with computing. | Term 1 | AB/AS | N/A | 16.9.2021 |
| Issue continuity and progression of skills document to all staff | Term 1 | AB/AS | Document/National Curriculum | 21.09.2021 |
| Issue a questionnaire to staff to gauge confidence with teaching computing/where any issues lie. | Term 1 | AB/AS | AB to complete questionnaire | Incomplete |
| Organise training based on the results from the questionnaire. | Term 2/3 | AB/AS | SAS | November 22 |
| To take an inventory of all the hardware/software that school has | Term 2/3 | AB | Time | July 22 |
| Organise a trip for Year 5/6 to apply some of the programming skills that are being taught | Term 2/3 | AB | A company to do this | Incomplete |
| Look at computing MTP across the school | Term 3 | AB | Time | Incomplete |